## Anomalies
Octant | Ring | PPB1 | Cavern | Rack | Ch | pp | Anomaly | Action | Repair | Comment
1 | Inner | B5 P3 | US15 | 23-15/3 | 14 | -4 | HVRET - VddRet 11k | y | ? (no) | probe at PPB1; unlikely to repair
1 | Outer | B3 P1 | US15 | 05-14/4 | 1 | 5 | Temp1-VddRet open circuit | y | ? (no) | probe at PPB1; unlikely to repair
1 | Outer | B3 P1 | US15 | 05-14/4 | 11 | -6 | VVCSEL-VddRet - 137k | ? | ? | Module 6, may be possible to repair
1 | Outer | B3 P1 | US15 | 05-14/4 | 11 | -6 | HVRet wire broken | y | ? | probe at PPB1; add wire HVRET to VccRetSense if necessary
1 | Outer | B3 P2 | US15 | 23-15/1 | 10 | 5 | sense wire repair | n | SR1 | VddRetSense wired to VddRet at PPB1
1 | Outer | B4 P1 | US15 | 05-14/3 | 11 | -6 | SELECT-VddRet - 3.96k | n | N/A
1 | Outer | B4 P2 | US15 | 23-15/2 | 0 | -6 | SELECT-VddRet - 3.94k | n | N/A | Known from SR1 (but logged there as 5 ohm)
1 | Outer | B4 P2 | US15 | 23-15/2 | 9 | 4 | VVCSEL-VddRet - 137k | n | ? | Known from Oxford
1 | Outer | B5 P5 | US15 | 23-15/3 | 47 | 6 | SELECT-VddRet - 4.84k | n | N/A
1 | Outer | B5 P6 | US15 | 24-15/3 | 11 | 6 | SELECT-VddRet - 4.74k | n | N/A
2 | Inner | B4 P6 | US15 | 24-15/2 | 0 | -6 | VddRet and VccRet sense o/c | n | 2006-11-17 | Fixed by adding wires at PPB1 (PWP 17/11/2006)
2 | Inner | B5 P11 | US15 | 27-15/1 | 35 | -6 | VVCSEL-VddRet - 136k | ? | ? | Module 6, may be possible to repair
2 | Inner | B6 P9 | US15 | 23-15/4 | 43 | 2 | VVCSEL-VddRet - 136k | n | ? | Known from Oxford
2 | Outer | B3 P6 | US15 | 24-15/1 | 9 | 4 | sense wire repair | n | SR1 | VddRetSense wired to VddRet at PPB1
2 | Outer | B4 P10 | US15 | 24-15/1 | 44 | 3 | sense wire repair? | y | ? | Vdd Loop test at SR1 53 ohm. Was this fixed?
2 | Outer | B4 P7 | US15 | 24-15/2 | 18 | 1 | VVCSEL-VddRet - 8.32k | n | N/A | We do not understand the value of this measurement!
2 | Outer | B4 P8 | US15 | 24-15/2 | 24 | -6 | SELECT-VddRet - 917Ohms | n | N/A | Known from SR1 (but logged there as 660 ohm)
2 | Outer | B4 P8 | US15 | 24-15/2 | 34 | 5 | sense wire repair? | y | ? | Vcc Loop test at SR1 20Mohm. Was this fixed?
2 | Outer | B5 P12 | US15 | 27-15/1 | 20 | -3 | SELECT-VddRet - 4.81k | n | N/A
2 | Outer | B5 P12 | US15 | 27-15/1 | 21 | -4 | SELECT-VddRet - 4.87k | n | N/A
2 | Outer | B5 P7 | US15 | 24-15/3 | 19 | 2 | Vcc-VccSense - 176Ohms | y | ? | probe at PPB1; add wire Vcc to VccSense if necessary
2 | Outer | B5 P8 | US15 | 24-15/3 | 24 | -6 | SELECT-VddRet - 2.67k | n | N/A
2 | Outer | B5 P8 | US15 | 24-15/3 | 25 | -5 | SELECT-VddRet - 2.67k | n | N/A
3 | Inner | B4 P15 | USA15 | 26-11/2 | 13 | 5 | VPIN-VddRet -3.17V | n | no | use redundancy
3 | Inner | B5 P14 | USA15 | 22-14/1 | 1 | 5 | HVRET-VddRet | n | 2006-11-17 | Fixed by adding wire at PPB1
3 | Inner | B6 P16 | USA15 | 22-14/3 | 26 | -4 | VVCSEL-VddRet 136kOhm | ? | ? | new defect
3 | Inner | B6 P17 | USA15 | 22-14/3 | 46 | 5 | VVCSEL-VddRet 136kOhm | n | ? | Known from Oxford
3 | Outer | B4 P13 | USA15 | 26-11/4 | 6 | -1 | sense wire repair | n | RAL | Vcc-VccSense wired at PPB1 during harness production
3 | Outer | B4 P14 | USA15 | 26-11/2 | 34 | -5 | sense wire repair | n | RAL | Vcc-VccSense wired at PPB1 during harness production
4 | Inner | B4 P16 | USA15 | 26-11/2 | 6 | -1 | SELECT - VddRet 4.94k | n | N/A
4 | Inner | B4 P16 | USA15 | 26-11/2 | 9 | -4 | HVRet-VddRet=18.9Ohms | y | ? | Look for evidence of deliberate repair at PPB1
4 | Inner | B6 P28 | USA15 | 28-11/4 | 31 | 2 | HVRet-VddRet=18.9Ohms | y | ? | Look for evidence of deliberate repair at PPB1
5 | Outer | B3 P17 | USA15 | 29-14/2 | 30 | 1 | sense wire repairs | n | SR1 | 3 wires: HVRET -VccRetSense; VddRetSense-VddRet; VddSense-Vdd
5 | Outer | B3 P17 | USA15 | 29-14/2 | 31 | 2 | sense wire repairs | n | SR1 | 1 wire: VccRetSense-VccRet . C04 => 0ohm (VddRetSense - Vdd)
5 | Outer | B3 P17 | USA15 | 29-14/2 | 35 | 6 | sense wire repairs | n | SR1 | 2 wires: VccSense - Vcc; VddSense - Vdd
6 | Inner | B6 P39 | USA15 | 25-11/4 | 18 | 1 | sense wire repair? | y | SR1 | VccSense wired to Vcc at PPB1?
6 | Inner | B6 P40 | USA15 | 25-11/4 | 29 | -1 | sense wire repair | n | Oxford | VddSense wired to VddSense at PPB1
6 | Outer | B4 P27 | USA15 | 25-11/2 | 19 | 2 | sense wire repair | n | RAL | Vdd-VddSense wired at PPB1 during harness production
7 | Inner | B6 P49 | US15 | 29-15/3 | 42 | 1 | sense wire repair? | y | SR1 | VccSense wired to Vcc at PPB1?
8 | Inner | B6 P51 | US15 | 28-15/4 | 0 | 6 | sense wire repair | n | Oxford | VddSense wired to VddSense at PPB1
8 | Outer | B3 P32 | US15 | 05-14/4 | 21 | -4 | sense wire repair | n | SR1 | HVRET wired to VccRetSense at PPB1
8 | Outer | B5 P44 | US15 | 28-15/4 | 28 | 2 | sense wire repair? | y | ? | Vcc Loop test at SR1 13ohms. Was this fixed?