## SCT type 4 length on USA side
|  | SCT type 4 cables, USA side | [16 empty] | CABLE received
The given length includes the length inside both PP3 and LV racks: 2m inside PP3 + between racks + 2.5 m inside LV rack | [14 empty] | The given length includes the length inside both PP3 and LV racks: 2m inside PP3 + between racks + 2.5 m inside LV rack
[19 empty] | 2005-10-20 | 2005-10-26 | 2005-11-16 | 2006-12-09 | 2006-02-24 | 2006-03-01 | 2006-03-08 | 2006-03-13 | 2006-03-15 | 2006-03-16 | 2006-03-21 | 2006-03-24 | 2006-03-28 | 2006-03-29 | 2006-04-05 | 2006-04-06 | 2006-04-12 | 2006-04-27 | 2006-05-04 | cables missing
UX rack | USA rack | Cables exit the PP3 rack on Top/Bottom | Configuration see fig. below | tray in UX15 | tray in TE16 | number of cables in bundle | spares | spares (in the middle) | total (double harness) | Calculated length between racks, m | Contingensy, m | TOTAL LENGTH, m | TOTAL LENGTH, m | Total length of raw cables, km | UX rack | USA rack | TOTAL LENGTH, m | Prioririty | pieces (but we use them as single cables) | [18 empty] | cables | pieces |  | total length missing | length minus 1 meter | total length (if minus 1 meter)
Y.51-23.X8 | Y.26-11.A2 | Top | 2 | CT/X.RC1.S7-9/6L1-2 | CT/TE16.RC1T12-A2/6L1-5 | 192 | 6 |  | 99 | 61 | 4 | 65 | 130 | 12.87 | Y.51-23.X8 | Y.26-11.A2 | 130 | 6 | [10 empty] | 3 | 16 | 64 | 16 | [5 empty] | 0 | 0 |  | 0 | 64 | 12.672
Y.52-23.X8 | Y.22-14.A2 | Top | 4 | CT/X.RC1.S7-9/6L2-2 | CT/TE16.RC1T22-A2/6L1-7 | 188 | 6 | 1 | 97 | 71 | 4 | 75 | 150 | 14.55 | Y.52-23.X8 | Y.22-14.A2 | 150 | 6 | [14 empty] | 56 | 41 |  |  |  | 0 | 0 |  | 0 | 74 | 14.356
Y.53-23.X8 | Y.27-11.A2 | Top | 2 | CT/X.RC1.S7-9/6L1-3 | CT/TE16/RC1T13-A2/6L1-6 | 188 | 2 | 7 | 95 | 63.6 | 4 | 67.6 | 135.2 | 12.844 | Y.53-23.X8 | Y.27-11.A2 | 135.2 | 6 | [15 empty] | 7 | 44 | 32 | 12 | 0 | 0 |  | 0 | 66.6 | 12.654
Y.51-26.X5 | Y.23-14.A2 | Top | 4 | CT/X.RC1.S9-11/6L2-3 | CT/TE16/RC1T23-A2/6L1-8 | 184 | 6 | 3 | 95 | 63.4 | 4 | 67.4 | 134.8 | 12.806 | Y.51-26.X5 | Y.23-14.A2 | 134.8 | 4 |  |  |  | 32 |  | 10 | 19 | 34 | [11 empty] | 0 | 0 |  | 0 | 66.4 | 12.616
Y.51-26.X5 | Y.29-11.A2 | Top | 2 | CT/X/RC2/S9-11/6L1-2 | CT/TE16/RC2T12-A2/6L2-6 | 92 |  | 1 | 46 | 58.8 | 4 | 62.8 | 125.6 | 5.7776 | Y.51-26.X5 | Y.29-11.A2 | 125.6 | 4 | [5 empty] | 20 |  | 22 | 3 |  |  | 1 | [7 empty] | 0 | 0 |  | 0 | 61.8 | 5.6856
Y.53-26.X5 | Y.29-11.A2 | Top | 2 | CT/X/RC2/S9-11/6L1-2 | CT/TE16/RC2T12-A2/6L2-6 | 94 |  |  | 47 | 57 | 4 | 61 | 122 | 5.734 | Y.53-26.X5 | Y.29-11.A2 | 122 | 5 | [8 empty] | 47 | [10 empty] | 0 | 0 |  | 0 | 60 | 5.64
Y.53-26.X5 | Y.28-11.A2 | Top | 2 | CT/X/RC2/S9-11/6L2-2 | CT/TE16/RC2T22-A2/6L2-5 | 182 | 8 |  | 95 | 63 | 4 | 67 | 134 | 12.73 | Y.53-26.X5 | Y.28-11.A2 | 134 | 5 | [8 empty] | 22 | 40 | 33 | [8 empty] | 0 | 0 |  | 0 | 66 | 12.54
Y.52-25.X2 | Y.25-11.A2 | Top | 2 | CT/DPC.RC1B12-TE16/6L1-2 | CT/TE16/RC1B12-A2/6L1-2 | 192 | 6 |  | 99 | 46.6 | 3 | 49.6 | 99.2 | 9.8208 | Y.52-25.X2 | Y.25-11.A2 | 99.2 | 2 |  |  | 99 | [16 empty] | 0 | 0 | x | 0 | 48.6 | 9.6228
Y.52-25.X2 | Y.28-14.A2 | Top | 1 | CT/DPC.RC1B22-TE16/6L2-9 | CT/TE16/RC1B22-A2/6L2-9 | 96 | 6 |  | 51 | 49.6 | 3 | 52.6 | 105.2 | 5.3652 | Y.52-25.X2 | Y.28-14.A2 | 105.2 | 2 |  | 20 | 41 | [16 empty] | 0 | 0 | x | 0 | 51.6 | 5.2632
Y.53-25.X2 | Y.28-14.A2 | Bottom | 3 | CT/DPC.RC1B22-TE16/6L2-9 | CT/TE16/RC2T12-A2/6L2-9 | 96 | 6 |  | 51 | 47.8 | 2.5 | 50.8 | 101.6 | 5.1816 | Y.53-25.X2 | Y.28-14.A2 | 101.6 | 3 |  |  | 15 |  |  |  | 36 | [12 empty] | 0 | 0 |  | 0 | 49.8 | 5.0796
Y.53-25.X2 | Y.29-14.A2 | Bottom | 3 | CT/DPC.RC2T22-TE16/6L2-7 | CT/TE16/RC2T22-A2/6L2-7 | 192 | 6 | 4 | 99 | 48 | 2.5 | 51 | 102 | 10.098 | Y.53-25.X2 | Y.29-14.A2 | 102 | 3 |  |  |  |  | 20 | 50 | 29 | [12 empty] | 0 | 0 |  | 0 | 50 | 9.9
Y.51-25.X1 | Y.26-14.A2 | Bottom | 3 | CT/DPC.RC2B22-TE16/6L2-1 | CT/TE16/RC2B22-A2/6L2-1 | 182 | 2 | 2 | 92 | 44.1 | 2.5 | 47.1 | 94.2 | 8.6664 | Y.51-25.X1 | Y.26-14.A2 | 94.2 | 1 | 91 | 93 | [17 empty] | 0 | 0 | x | 0 | 46.1 | 8.4824
Y.51-25.X1 | Y.27-14.A2 | Bottom | 3 | CT/DPC.RC2B22-TE16/6L2-2 | CT/TE16/RC2B22-A2/6L2-2 | 116 | 2 | 1 | 59 | 46.1 | 2.5 | 49.1 | 98.2 | 5.7938 | Y.51-25.X1 | Y.27-14.A2 | 98.2 | 1 |  | 42 | 38 | [16 empty] | 0 | 0 | x | 0 | 48.1 | 5.6758
Y.53-23.X8 | Y.27-14.A2 | Top | - | CT/X.RC1.S7-9/6L1-2 | CT/TE16.RC1T12-A2/6L1-5 | 24 | 2 | 1 | 13 | 67.4 | 4 | 70.4 | 140.8 | 1.8304 | Y.53-23.X8 | Y.27-14.A2 | 140.8 | 6 | [10 empty] | 12 |  | 1 | [6 empty] | 0 | 0 |  | 0 | 69.4 | 1.8044
Y.51-26.X5 | Y.27-14.A2 | Top | - | CT/X/RC2/S9-11/6L1-2 | CT/TE16/RC2T12-A2/6L2-6 | 24 |  | 1 | 12 | 64 | 4 | 67 | 134 | 1.608 | Y.51-26.X5 | Y.27-14.A2 | 134 | 4 | [16 empty] | 12 |  |  | 0 | 0 |  | 0 | 66 | 1.584
Y.53-26.X5 | Y.27-14.A2 | Top | - | CT/X/RC2/S9-11/6L2-2 | CT/TE16/RC2T22-A2/6L2-5 | 24 |  | 1 | 12 | 67.6 | 4 | 71.6 | 143.2 | 1.7184 | Y.53-26.X5 | Y.27-14.A2 | 143.2 | 5 |  |  |  | 12 | [15 empty] | 0 | 0 |  | 0 | 70.6 | 1.6944
Y.52-25.X2 | Y.27-14.A2 | Top | - | CT/DPC.RC1B22-TE16/6L2-9 | CT/TE16/RC1B22-A2/6L2-9 | 0 | 0 | 0 | 0 | 50.2 | 3 | 54.2 | 108.4 | 0 | Y.52-25.X2 | Y.27-14.A2 | 108.4 |  | 91 | 155 | 193 | 44 | 20 | 80 | 84 | 56 | 72 | 40 | 48 | 17 | 65 | 16 | 56 | 48 | 56 | 32 | 12
[14 empty] | 127.3942 |  |  |  |  | 91 | 155 | 386 | 88 | 40 | 160 | 168 | 112 | 144 | 80 | 96 | 34 | 130 | 32 | 112 | 96 | 112 | 64 | 24 | 0 | 0 |  | 0 |  | 125.2702
[6 empty] | 2066 | 58 | 22 | 1062
[20 empty] | 75 | 50m | [7 empty] | 141 m were shipped as 143m |  |  | cables |  |  |  |  | received | 2124 | 1062
[19 empty] | it was | 20 | 53m
[20 empty] | 59 | 49m
[20 empty] | 1 | 47m | [14 empty] | actual pieces received |  |  | 1185
because firse 2 shipments used as single cables
Note on AE18: : 141 m were shipped as 143m
cable Layer 1
cable Layer 2
LV rack in USA15
PP3 rack in UX15,
Cables routed through top of rack
cable Layer 1
cable Layer 2
LV rack in USA15
PP3 rack in UX15,
Cables routed through bottom of rack
Fig 1. Cable layout between the racks
Y.52-25.X2 - Y.28-14.A2
Fig 3. Cable layout between the racks
Y.53-25.X2 - Y.28-14.A2
Y.53-25.X2 - Y.29-14.A2
Y.51-25.X1 - Y.26-14.A2
Y.51-25.X1 - Y.27-14.A2
Length of cables in layer 1 is
close to the length in layer 2
Length of cables in layer 1 is close to the length in layer 2
cable Layer 1
cable Layer 2
LV rack in USA15
PP3 rack in UX15,
Cables routed through top of rack
Fig 2. Cable layout between the racks
Y.51-23.X8 - Y.26-11.A2
Y.53-23.X8 - Y.27-11.A2
Y.51-26.X5 - Y.29-11.A2
Y.53-26.X5 - Y.29-11.A2
Y.53-26.X5 - Y.28-11.A2
Y.52-25.X2 - Y.25-11.A2
Length of cables in layer 2 is
up to 3.5m longer than the length in layer 1
cable Layer 1
cable Layer 2
LV rack in USA15
PP3 rack in UX15,
Cables routed through top of rack
Fig 4. Cable layout between the racks:
Y.52-23.X8 - Y.22-14.A2
Y.51-26.X5 - Y.23-14.A2
Length of cables in layer 2 is
up to 3.5m longer than the length in layer 1

## Schema UX-USA
USA15
22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | RACKS in USA15
[10 empty] | 160 |  |  |  |  | 14
11
| 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29
1
1
2
[13 empty] | 2 |  |  | CABLE TRAYS (end point in USA15 .2)
3
3
4
4
5
5
6
6
7
7
8
8
9
9
10
10
11
11
| Y.51-23.X8 | Y.52-23.X.8 | Y.53-23.X8 | [11 empty] | UX15
[6 empty] | Y.51-26.X5 | Y.53-26.X5
[10 empty] | Y.52-25.X2 | Y.53-25.X2
Y.51-25.X1
| 208 | 192 | 192
[6 empty] | 304 | 304
[10 empty] | 304 | 288
288
192
16
96
192
16
96
192
16
96
96
192
16
192
192
96
192
192

## Installation
| UX rack | PS racks | Barrel/ Endcap | sector | Cables exit the PP3 rack on Top/ Bottom | Cables entering USA racks Top/ Bottom | PS Crates c1=top c4= bottom | C4 | C3 | C2 | C1 | priority for connector in situ | priority for connection to PS
| Y.51-23.X8 | Y.26-11.A2 | B | 7 | Top | Bottom | c1,c2,c3,c4 | B | B | B | B | 1 | 3
| Y.52-23.X8 | Y.22-14.A2 | B/E | 7 | Top | Bottom | c1,c2,c3,c4 | E | B | B | B | 1 | 3
| Y.53-23.X8 | Y.27-11.A2 | E | 7 | Top | Bottom | c1,c2,c3,c4 | E | E | E | E | 4 | 6
| Y.51-26.X5 | Y.23-14.A2 | E | 9 | Top | Bottom | c1,c2,c3,c4 | E | E | E | E | 4 | 6
USA | Y.51-26.X5 | Y.29-11.A2 | B/E | 9 | Top | Bottom | c1,c2 |  |  | E | B | 2 | 4
| Y.53-26.X5 | Y.29-11.A2 | B/E | 9 | Top | Bottom | c3,c4 | E | B
| Y.53-26.X5 | Y.28-11.A2 | B/E | 9 | Top | Bottom | c1,c2,c3,c4 | B | B | E | E | 2 | 4 | ++
| Y.52-25.X2 | Y.25-11.A2 | B | 11 | Top | Bottom | c1,c2,c3,c4 | B | B | B | B | 1 | 5 | +++
| Y.52-25.X2 | Y.28-14.A2 | B | 11 | Top | Bottom | c1,c2(24),c3(12),c4(12) | B | B | B | B | 2 | 4 | +
| Y.53-25.X2 | Y.28-14.A2 | B | 9 | Bottom | Bottom | c2(24),c3(36),c4(36) | B | B | B |  |  | 4
| Y.53-25.X2 | Y.29-14.A2 | B/E | 9 | Bottom | Bottom | c1,c2,c3,c4 | E | E | B | B | 3 | 4
| Y.51-25.X1 | Y.26-14.A2 | B/E | 11 | Bottom | Bottom | c1,c2,c3,c4 | E | E | E | B | 3 | 5
| Y.51-25.X1 | Y.27-14.A2 | E | 11 | Bottom | Bottom | c1,c2,c3(24) |  | E | E | E | 4 | 6
| Y.53-23.X8 | Y.27-14.A2 | E | 7 | Top | Bottom | c4(24) | E |  |  |  |  | 6
| Y.51-26.X5 | Y.27-14.A2 | E | 9 | Top | Bottom | c4(24) | E |  |  |  |  | 6
| Y.53-26.X5 | Y.27-14.A2 | E | 9 | Top | Bottom | c3(24) |  | E |  |  |  | 6
+ | priority 4 because bottom crates are shared with sector 9
++ | top 2 crates can be connected later
+++ | priority 1 for connector in situ because of vicinity to fibres rack
| UX rack | PS racks | Barrel/ Endcap | sector | Cables exit the PP3 rack on Top/ Bottom | Cables entering USA racks Top/ Bottom | PS Crates c1=top c4= bottom | C4 | C3 | C2 | C1 | priority for connector in situ | priority for connection to PS
| Y.37-01.X6 | Y.05-14.S2 | B | 1 | Top | Botttom | c1,c2,c3,c4 | B | B | B | B |  | 1
| Y.43-01.X6 | Y.10-15.S2 | E | 1 | Top | Bottom | c1,c2,c3,c4 | E | E | E | E |  | 6
| Y.43-01.X6 | Y.11-15.S2 | E | 1 | Top | Bottom | c1,c2(24) |  |  | E | E |  | 6
| Y.47-01.X6 | Y.11-15.S2 | E | 1 | Top | Bottom | c2(24),c3,c4 | E | E | E |  |  | 6
US | Y.43-01.X6 | Y.12-15.S2 | B | 1 | Top | Bottom | c1(24) |  |  |  | B |  | 1
| Y.47-01.X6 | Y.12-15.S2 | B/E | 1 | Top | Bottom | c1(24),c2,c3,c4 | E | E | E | B |  | 1
| Y.52-01.X6 | Y.23-15.S2 | B | 1 | Top | Bottom | c1(24), c2(36),c3(36) |  | B | B | B |  | 1
| Y.52-04.X7 | Y.23-15.S2 | B | 3 | Bottom | Bottom | c1(24),c2(12),c3(12),c4 | B | B | B | B |  |  | *
| Y.52-04.X7 | Y.24-15.S2 | B | 3 | Bottom | Top | c1,c2,c3,c4 | B | B | B | B |  | 2
| Y.53-04.X7 | Y.25-15.S2 | E | 3 | Bottom | Top | c1,c2,c3,c4 | E | E | E | E |  | 6
| Y.53-02.X2 | Y.26-15.S2 | E | 15 | Top | Bottom | c1,c2,c3,c4 | E | E | E | E |  | 6
| Y.51-02.X2 | Y.27-15.S2 | E | 15 | Top | Top | c3(24),c4 | E | E |  |  |  | 6
| Y.53-04.X7 | Y.27-15.S2 | B/E | 3 | Bottom | Top | c1,c2,c3(24) |  | E | E | B |  | 2 | **
| Y.51-02.X2 | Y.28-15.S2 | B | 15 | Top | Bottom | c2,c3,c4 | B | B | B |  |  | 1 | *
| Y.52-01.X6 | Y.28-15.S2 | B | 1 | Top | Bottom | c1 |  |  |  | B
| Y.52-02.X2 | Y.29-15.S2 | B | 15 | Top | Bottom | c1,c2,c3,c4 | B | B | B | B |  | 2
* | priority 1 because top crate(s) belongs to (shared with) sector 1
** | only top crate
2006-07-23

## testing
length | test date | serial | qty |  | tot | double
33m |  |  |  |  | 156 | 78
| 22.08.05 | 3300001-3300040 | 40 |  |  | 0
| 01.09.05 | 3300001-3300060 | 60 |  |  | 0
| 15.09.05 | 3300061-3300116 | 56 |  |  | 0
--------------------------------------------------------------------------------- | [5 empty] | 0
34m |  |  |  |  | 192 | 96
| 23.08.05 | 3400001-3400040 | 40 |  |  | 0
| 15.09.05 | 3400041-3400080 | 40 |  |  | 0
| 16.09.05 | 3400081-3400192 | 112 |  |  | 0
--------------------------------------------------------------------------------- | [5 empty] | 0
35m |  |  |  |  | 86 | 43
| 30.09.05 | 3500001-3500042 | 42 |  |  | 0
| 05.10.05 | 3500043-3500078 | 36 |  |  | 0
|  | 3500081-3500086 | 6 |  |  | 0
|  | 3500089-3500090 | 2 |  |  | 0
--------------------------------------------------------------------------------- | [5 empty] | 0
46m |  |  |  |  | 182 | 91
| 22.09.05 | 4600001-4600028 | 28 |  |  | 0
|  | 4600031-4600060 | 30 |  |  | 0
| 29.09.05 | 4600061-4600124 | 64 |  |  | 0
| 30.09.05 | 4600125-4600184 | 60 |  |  | 0
--------------------------------------------------------------------------------- | [5 empty] | 0
47m |  |  |  |  | 182 | 91
| 21.10.05 | 4700001-4700180 | 180 |  |  | 0
| 28.10.05 | 4700181-4700182 | 2 |  |  | 0
--------------------------------------------------------------------------------- | [5 empty] | 0
49m |  |  |  |  | 118 | 59
| 28.10.05 | 4900001-4900118 | 118 |  |  | 0
--------------------------------------------------------------------------------- | [5 empty] | 0
50m |  |  |  |  | 150 | 75
| 28.10.05 | 5000001-5000150 | 150 |  |  | 0
------------------------------------------------------------------------------------- | [5 empty] | 0
51m |  |  |  |  | ? | #VALUE!
| 22.09.05 | 5100053-5100120 | 68 |  |  | 0
---------------------------------------------------------------------------------- | [5 empty] | 0
52m |  |  |  |  | 76 | 38
| 21.09.05 | 5200001-5200052 | 52 |  |  | 0
| 22.09.05 | 5200121-5200144 | 24 |  |  | 0
---------------------------------------------------------------------------------- | [5 empty] | 0
53m |  |  |  |  | 30 | 15
| 13.10.05 | 5300001-5300008 | 8 |  |  | 0
| 02.11.05 | 5300009-5300030 | 22 |  |  | 0
----------------------------------------------------------------------------------- | [5 empty] | 0
57m |  |  |  |  | 200 | 100
| 25.08.05 | 5700001-5700120 | 120 |  |  | 0
| 14.09.05 | 5700121-5700192 | 72 |  |  | 0
| 13.10.05 | 5700193-5700200 | 8 |  |  | 0
----------------------------------------------------------------------------------- | [5 empty] | 0
61m |  |  |  |  | 64 | 32
| 29.09.05 | 6100001-6100064 | 64 |  |  | 0
| 13.10.05 | 6100065 |  | ? |  | 0
----------------------------------------------------------------------------------
USA
---------------------------------------------------------------------------------- | [5 empty] | 0
98m |  |  |  |  | 76 | 38
| 16.11.05 | 9800001-9800076 | 76 |  |  | 0
----------------------------------------------------------------------------------- | [5 empty] | 0
99m |  |  |  |  | 198 | 99
| 16.11.05 | 9900001-9900040 | 40 |  |  | 0
| 16.11.05 | 9900041-9900100 | 60 |  |  | 0
| 18.11.05 | 9900101-9900138 | 38 |  |  | 0
| 22.11.05 | 9900139-9900162 | 24 |  |  | 0
|  | 9900165-9900198 | 34 |  |  | 0
| 22.11.05 | 9900164-9900165 | 2 |  |  | 0
----------------------------------------------------------------------------------- | [5 empty] | 0
102m |  |  |  |  | 296 | 148
| 18.11.05 | 1020001-1020016 | 16 |  |  | 0
| 22.11.05 | 1020017-1020030 | 14 |  |  | 0
| 08.03.06 | 1020001-1020090 |  |  |  | 0
| 08.03.06 | 1020091-1020142 | 142 |  |  | 0
| 10.03.06 | 1020147-1020148 | 2 |  |  | 0
|  | 1020151-1020152 | 2 |  |  | 0
| 10.03.06 | 1020155-1020178 | 24 |  |  | 0
|  | 1020181-1020236 | 56 |  |  | 0
| 13.03.06 | 1020237-1020256 | 20 |  |  | 0
| 16.03.06 | 1020257-1020276 | 20 |  |  | 0
---------------------------------------------------------------------------------- | [5 empty] | 0
105m |  |  |  |  | 82 | 41
| 16.11.05 | 1050001-1050042 | 42 |  |  | 0
| 17.11.05 | 1050043-1050046 | 4 |  |  | 0
|  | 1050049-1050082 | 34 |  |  | 0
| 22.11.05 | 1050048-1050049 | 2 |  |  | 0
122m |  |  |  |  | 92 | 46
| 19.04.06 |  | 26
| 20.04.06 |  | 66
---------------------------------------------------------------------------------- | [5 empty] | 0
126m |  |  |  |  | 84 | 42
| 13.03.06 | 1260001-1260006 | 6 |  |  | 0
| 13.03.06 | 1260007-1260084 | 78 |  |  | 0
---------------------------------------------------------------------------------- | [5 empty] | 0
130m |  |  |  |  | 72 | 36
| 27.03.06 | 1300001-1300006 | 6 |  |  | 0
| 27.03.06 | 1300007-1300038 | 32 |  |  | 0
| 03.04.06 | 1301301-1301334 | 34 |  |  | 0
---------------------------------------------------------------------------------- | [5 empty] | 0
134m |  |  |  |  | 184 | 92
| 16.12.05 | 1340001-1340024 | 24 |  |  | 0
| 23.03.06 | 1340001-1340016 | 16 |  |  | 0
| 23.03.06 | 1340017-1340026 | 10 |  |  | 0
|  | 1430025-1430026 | 2 |  |  | 0
| 24.03.06 | 1340027-1340040 | 14 |  |  | 0
|  | 1340043-1340054 | 12 |  |  | 0
|  | 1340057-1340058 | 2 |  |  | 0
| 27.03.06 | 1340055-1340056 | 2 |  |  | 0
|  | 1340059-1340066 | 8 |  |  | 0
| 30.03.06 | 1340067-1340098 | 32 |  |  | 0
| 18.04.06 |  | 52
| 20.04.06 |  | 10
-------------------------------------------------------------------------------- | [5 empty] | 0
135 m |  |  |  |  | 190 | 95
| 16.12.05 | 1350001-1350048 | 48 |  |  | 0
| 01.02.06 | 1350049-1350064 | 16 |  |  | 0
| 10.03.06 | 1350143-1350146 | 4 |  |  | 0
|  | 1350149-1350150 | 2 |  |  | 0
| 13.03.06 | 1350065-1350096 | 32 |  |  | 0
| 13.03.06 | 1350097-1350100 | 4 |  |  | 0
| 16.03.06 | 1350101-1350120 | 20 |  |  | 0
| 21.03.06 | 1350113-1350176 | 64 |  |  | 0
-------------------------------------------------------------------------------- | [5 empty] | 0
141m |  |  |  |  | 2 | 1
| 27.03.06 | 1410001-1410002 | 2 |  |  | 0
--------------------------------------------------------------------------------- | [5 empty] | 0
143m |  |  |  |  | 24 | 12 | USA | 650
| 23.03.06 | 1430001-1430024 | 24 |  |  | 0
0
0
0