## Main Schedule
SCT Cables and Patch Panels - 1-June |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July
|  |  |  | 2006-04-03 | 2006-04-10 | 2006-04-17 | 2006-04-24 | 2006-05-01 | 2006-05-08 | 2006-05-15 | 2006-05-22 | 2006-05-29 | 2006-06-05 | 2006-06-12 | 2006-06-19 | 2006-06-26 | 2006-07-03 | 2006-07-10 | 2006-07-17
Type IV |  | French team |  | 2006-04-17: 63; 2006-04-24: 63; 2006-05-01: 56; 2006-05-08: 63; 2006-05-15: 63; 2006-05-22: 60; 2006-05-29: 80
Installation |  | Russian team | 452 | 2006-04-17: 50; 2006-04-24: 100; 2006-05-01: 100; 2006-05-08: 100; 2006-05-15: 100; 2006-06-26: 774
Acceptance |  |  |  | 2 shifts | * | Japan | Japan | * | * | * | * | * | Manchester | Tomas | Tomas
|  |  |  | * | * | Japan | Japan | * | * | * | * | * | Manchester | Sinica | Sinica
Test in rack after installation | [6 empty] | * | * | Japan | Lancaster | * | * | * | * | * |  |  |  | *
[7 empty] | * | * | Japan | Lancaster | * | * | * | * | * |  |  |  | *
Connector in situ by external company - CPE |  |  |  | 2006-05-22: 200; 2006-07-17: 1924
Test of cut cables with connector |  |  |  | Petr | Petr | Petr |  | * | * |  |  |  |  | * | * | * | * | *
|  |  |  | * | Freiburg | * | * | * | * |  |  |  |  | * | * | * | * | *
Plug-in cables into PS crates + test | [6 empty] | Freiburg |  |  | Petr | Petr | Petr | * | * | * | Petr | Petr | Petr | Petr
|  |  |  | Edward |  |  | Petr | Petr | Petr | Prague | Prague | Freiburg | * | * | * | Freiburg | * | Prague | Prague
|  |  |  | Stefan |  |  | JanB | JanB | JanB | JanB | JanB | JanB | * | * | * | * | * | Prague | Prague
Type II-III | [6 empty] | JanB: 1946
Installation | [5 empty] | 616 | 262 | 108 | 240 | 240 | 240 | 240 | [6 empty] | 2142
Preparation |  |  |  | Vlasti | Vlasti | Vlasti | Vlasti | Vlasti | Vlasti | Vlasti | Vlasti | Sinica | Tomas | * | * | Tomas | Tomas | * | *
Acceptance + organize cables for installation |  |  |  | Martin | Freiburg | * | Geneva | Geneva | Geneva | Geneva | Geneva | Jessica | Jessica | * | * | Jessica | Jessica | Jessica | *
Folding of shield |  |  |  | * | * | * | Geneva | Geneva | Geneva | Geneva | Geneva | Freiburg | Sinica | * | * | Sinica | * | * | *
|  |  |  | * | * | Neil | Glasgow | Japan | Glasgow | Freiburg | * | * | Lancaster | * | * | Freiburg | * | * | *
|  |  |  | * | * | * | Glasgow | Japan | Glasgow | Freiburg | * | * | Lancaster | * | * | * | * | * | *
[7 empty] | Freiburg | Sinica | Sinica | Sinica | Sinica | * | Manchester | * |  |  | * | * | *
[7 empty] | Freiburg | TomB | * | * | * | * | Manchester | * |  |  | * | * | *
Mounting dPPB1 & dPPF1
Barrel: | Squeeze the cables to fit between pin and clamp holder |  |  | Lars | Lars | Lars | * | * | Lars | Lars | Lars
Plug-in to dPPB1, place the clamp, arrange drain wire |  |  |  | Neil | Neil | Neil | Neil | Neil | Neil | Neil | * | * | * | *
Endcap: | Crimping of drain wires, plug in the dPPF1 |  |  | * | * | * | * | * | Pieron | Pieron | Pieron | Pieron | Pieron | Pieron | Pieron | Pieron | Pieron | Pieron | Pieron
Test all cables installed in synch with installation |  |  |  | Martin | * | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | * | *
[7 empty] | JanB: Janice; JanB: Freiburg | Glasgow | Jessica | Jessica | Freiburg | * | * | *
[7 empty] | JanB: Freiburg | Glasgow | * | * | Freiburg | Martin | * | *
|  |  |  | * | * | * | * | * | * | Martin | Martin | * | * | * | * | * | * | * | *
PP3
Installation (most of the subracks already installed)
Test/Burn-in of units |  |  |  | Scott | Scott | Scott | [8 empty] | Scott | bar: JanB to JanB
Assembly into subracks |  |  |  | Edward +1 shift | Edward | Scott | [8 empty] | * | Scott | bar: JanB to JanB
Installation into racks/rework |  |  |  | Scott | Scott | Scott | * | * | * | MPI | MPI | * | * | * | Scott | Scott | Scott | Scott
Plug-in cables to PP3 |  |  |  |  | 1 shift | * | [6 empty] | * | * | * | MPI | MPI | * | * | bar: JanB to JanB
Type IV |  |  | as of March 10, 2100+ cables in US side and 602 cables in USA side already installed - 1522 cables to install since then
Type II-III |  |  | 4088 cables | 400 cables/week
Connector in situ by external company - CPE |  |  | as of March 10 almost all US side connectors built, to be completed before starting in USA side. Also rack 05 to be reworked, possibly by May 15
PP3 |  |  | as of April 20 most of the subracks assembled and installed - see PP3 sheet
done | to be done | part-time
Shits assignments are subject to change depending on people arrival/departure, people's skills, tester performance, cable arrival and change in priorities.

## PP3
|  |  |  | to be installed |  | to be assembled
US side
Y.51-02.X2 | 0 | subracks installed | 8 | Subracks in pit next to rack
Y.52-02.X2 | 7 | subracks installed |  | Cables 2043715 and 2043716 swapped.
Y.53-02.X2 | 7 | subracks installed
Y.37-01.X6 | 7 | subracks installed
Y.47-01.X6 | 10 | subracks installed
Y.43-01.X6 | 10 | subracks installed
Y.52-01.X6 | 5 | subracks installed
Y.52-04.X7 | 11 | subracks installed
Y.53-04.X7 | 10 | subracks installed
USA side
Y.51-25.X1 | 11 | subracks installed |  | Cables 2048000 and 2047999 swapped.
Y.53-25.X2 | 10 | subracks installed
Y 52-25.X2 | 0 | subracks installed | 10 | subracks in pit next to rack
Y.53-26.X5 | 10 | subracks installed |  |  | 1 | mini subrack
Y.51-26.X5 | 10 | subracks installed |  |  | 1 | mini subrack
Y.51-23.X8 | 4 | subracks installed | 2 | subracks in pit next to rack |  |  | 1 | special subrack
Y.52-23.X8 | 0 | subracks installed | 6 | subracks in pit next to rack |  |  | 1 | special subrack
Y.53-23.X8 | 0 | subracks installed | 3 | subracks in pit next to rack | 4 | standard subracks | 1 | special subrack