## Apr_Jul
SCT Cables and Patch Panels |  |  | 2006-06-21
[5 empty] | April |  |  |  | May |  |  |  | June |  |  |  |  | July
|  |  |  | 2006-04-03 | 2006-04-10 | 2006-04-17 | 2006-04-24 | 2006-05-01 | 2006-05-08 | 2006-05-15 | 2006-05-22 | 2006-05-29 | 2006-06-05 | 2006-06-12 | 2006-06-19 | 2006-06-26 | 2006-07-03 | 2006-07-10 | 2006-07-17 | 2006-07-24
Type IV |  | French team |  | 2006-04-17: 63; 2006-04-24: 63; 2006-05-01: 56; 2006-05-08: 63; 2006-05-15: 63; 2006-05-22: 60; 2006-05-29: 72 | 440
Installation |  | Russian team |  | 2006-04-03: 600; 2006-04-17: 50; 2006-05-01: 50; 2006-05-08: 50; 2006-05-15: 50; 2006-05-22: 50; 2006-05-29: 50; 2006-06-05: 70; 2006-06-12: 78 | 1048 | 636
Acceptance |  |  |  | 2 shifts | * | Japan | Japan | * | * | * | * | * | Manchester | * | Ken
|  |  |  | * | * | Japan | Japan | * | * | * | * | * | Manchester | * | Tomas
Test in rack after installation | [6 empty] | * | * | Japan | Lancaster | * | * | Glasgow | * | * | Petr |  |  | * | *
[7 empty] | * | * | Japan | Lancaster | * | * | Glasgow | * | * | Freiburg |  |  | * | *
Connector in situ by external company - CPE |  |  |  | 2006-05-22: 200 | 1924
Test of cut cables with connector |  |  |  | 2006-04-03: Petr; 2006-04-10: Petr; 2006-04-17: Petr; 2006-05-01: *; 2006-05-08: *
|  |  |  | * | Freiburg | * | * | * | *
Plug-in cables into PS crates + test | [6 empty] | Freiburg |  |  | Petr | Petr | Petr | * | * | * | Petr | Petr | Petr | Petr | Petr
Jan B
|  |  |  | Edward |  |  | Petr | Petr | Petr | Prague | Prague | Freiburg | * | * | * | Jan S | Jan Broz | Jan Broz | Jan Broz | Eva G
|  |  |  | Stefan |  |  | JanB | JanB | JanB | JanB | JanB | JanB | * | * | * | Jano H | Jano H |  |  | Anna M
Type II-III | [6 empty] | JanB: 2066 | 280 | 280 | 296 | 240 | 336 | 343 |  |  | 3841
Installation | [5 empty] | 616 | 262 | 108 | 280 | 260 | 280 | 260 | 280 | 280 | [6 empty] | 2626 | 1215
Preparation |  |  |  | Vlasti | Vlasti | Vlasti | Vlasti | Vlasti | Vlasti | Vlasti | Vlasti | Kuo-Ming | Tomas | Jessica | * | Tomas | Tomas | Tomas
Acceptance + organize cables for installation |  |  |  | Martin | Freiburg | * | Geneva | Geneva | Geneva | Geneva | Geneva | Jessica | Jessica | Katharine | * | * | * | *
Folding of shield |  |  |  | * | * | * | Geneva | Geneva | Geneva | Geneva | Geneva | Freiburg | Kuo-Ming | * | * | Kuo-Ming | Ken | Ken
|  |  |  | * | * | Neil | Glasgow | Japan | Glasgow | Freiburg | * | * |  | * | * | Freiburg | * | *
|  |  |  | * | * | * | Glasgow | Japan | Glasgow | Freiburg | * | * |  | * | * | Ken | * | *
[7 empty] | Freiburg | Kuo-Ming | Kuo-Ming | Kuo-Ming | Kuo-Ming | * | Manchester | * |  |  | * | *
[7 empty] | Freiburg | TomB | * | * | * | * | Manchester | * |  |  | * | *
Mounting dPPB1 & dPPF1
Barrel: | Squeeze the cables to fit between pin and clamp holder |  |  | Lars | Lars | Lars | * | * | Lars | Lars | Lars
Plug-in to dPPB1, place the clamp, arrange drain wire |  |  |  | Neil | Neil | Neil | Neil | Neil | Neil | Neil | * | * | * | *
Endcap: | Crimping of drain wires, plug in the dPPF1 |  |  | * | * | * | * | * | Jacek | Jacek | Jacek | Jacek | Jacek | Jacek | Jacek | Jacek | Jacek | Jacek
Test all cables installed in synch with installation |  |  |  | Martin | * | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre
[7 empty] | JanB: Janice; JanB: Freiburg | UCL | * | * | Freiburg | * | * | Tomas | Tomas
[7 empty] | JanB: Freiburg |  | Tomas | * | Freiburg | Martin | * | Ken | Ken
|  |  |  | * | * | * | * | * | * | Martin | Martin | * | * | Kuo-Ming | Kuo-Ming | * | * | * | *
PP3
Installation (most of the subracks already installed)
Test/Burn-in of units |  |  |  | Scott | Scott | Scott | [8 empty] | Scott | bar: JanB to JanB
Assembly into subracks |  |  |  | Edward +1 shift | Edward | Scott | [8 empty] | * | Scott | bar: JanB to JanB
Installation into racks/rework |  |  |  | Scott | Scott | Scott | * | * | * | MPI | MPI | * | * | Scott | Scott | Scott | Scott | Scott | Scott
Plug-in cables to PP3 |  |  |  |  | 1 shift | * | [6 empty] | * | * | * | MPI | MPI | * | * | bar: JanB to JanB
Type IV |  |  | as of March 10, 2100+ cables in US side and 602 cables in USA side already installed - 1522 cables to install since then
Type II-III |  |  | 4088 cables | 400 cables/week
Connector in situ by external company - CPE |  |  | as of March 10 almost all US side connectors built, to be completed before starting in USA side. Also rack 05 to be reworked, possibly by May 15
PP3 |  |  | as of April 20 most of the subracks assembled and installed - see PP3 sheet
done | to be done | part-time
Shits assignments are subject to change depending on people arrival/departure, people's skills, tester performance, cable arrival and change in priorities.
People longterm (currently) |  |  | start | end |  | start | JanB: end
Vlastik Kral |  | Prague | 2006-03-01 | 2006-05-30
Kuo-Ming Lee |  | Academia Sinica | 2006-05-08 | 2006-06-30
Alexandre Nadtochiy |  | Dubna | 2006-04-17 | 2006-09-18
Scott Moncrieff |  | Melboune | Feb | 2006-04-18 |  | 2006-06-12 | JanB: 2006-07-22
Jessica Metcalfe |  | UC Santa Cruz | 2006-05-29 | 2006-06-12
Ken Fowler |  | UC Santa Cruz | 2006-06-19 | 2006-08-14
Tomas Slavicek |  | Prague | 2006-06-05 | 2006-09-18
Petr Kubik |  | Prague | summer 2005 | 2006-06-05 |  | 2006-06-28 | JanB: 2006-09-30

## Aug_Sep
SCT Cables and Patch Panels |  |  | 2006-06-21
[5 empty] | August |  |  |  |  | September
|  |  |  | 2006-07-31 | 2006-08-07 | 2006-08-14 | 2006-08-21 | 2006-08-28 | 2006-09-04 | 2006-09-11 | 2006-09-18 | 2006-09-25
Type IV
Installation |  | Russian team |  | 2006-07-31: done
Test in rack after installation |  |  |  | 2006-07-31: Tomas; 2006-08-07: *; 2006-08-14: *
|  |  |  | Ken | * | *
Connector in situ by external company - CPE | [12 empty] | 1924 | bar: 2006-07-31 to 2006-08-21
Test of cut cables with connector |  |  |  |  | Petr | Petr | Petr | Petr | * | * | * | *
[5 empty] | Alexandre | Alexandre | Alexandre | * | * | * | * | *
Plug-in cables into PS crates + test |  |  |  | 2006-07-31: Petr; 2006-09-04: Petr; 2006-09-11: Petr; 2006-09-18: Petr; 2006-09-25: Petr
|  |  |  | Eva G |  |  |  | Eva G | Eva G | Jan S | Jan S
|  |  |  | Anna M |  |  |  | Anna M | Anna M
|  |  |  | Jan B |  |  |  | Jan B | Jan B
Type II-III |  |  |  | 2006-08-21: 247
Installation | [12 empty] | 247 | bar: 2006-08-21 to 2006-08-28
Preparation |  |  |  | 2006-08-07: Tomas; 2006-08-14: Tomas
Acceptance + organize cables for installation |  |  |  | 2006-08-07: Ken; 2006-08-14: *
Folding of shield | bar: 2006-08-07 to 2006-08-14
[5 empty] | * | *
[5 empty] | * | *
Mounting dPPB1 & dPPF1
Barrel: | Squeeze the cables to fit between pin and clamp holder | bar: 2006-08-21 to 2006-09-11
Plug-in to dPPB1, place the clamp, arrange drain wire |  |  |  | 2006-08-21: *; 2006-08-28: Neil; 2006-09-04: *; 2006-09-11: *
Endcap: | Crimping of drain wires, plug in the dPPF1 |  |  |  |  | Jacek | Jacek | Jacek | Jacek | Jacek | Jacek
Test all cables installed in synch with installation |  |  |  | 2006-08-21: Alexandre; 2006-08-28: Alexandre; 2006-09-04: Alexandre; 2006-09-11: Alexandre; 2006-09-18: Alexandre
[7 empty] | Tomas | Tomas |  |  | *
[7 empty] | * |  | * | * | *
[7 empty] | * | * | * | * | *
done | to be done | part-time
Shits assignments are subject to change depending on people arrival/departure, people's skills, tester performance, cable arrival and change in priorities.
People longterm
Alexandre Nadtochiy |  | Dubna
Tomas Slavicek |  | Prague
Petr Kubik |  | Prague
Jacek Jacek |  | Cracow

## PP3
|  |  |  | to be installed |  | to be assembled
US side
Y.51-02.X2 | 0 | subracks installed | 8 | Subracks in pit next to rack
Y.52-02.X2 | 7 | subracks installed |  | Cables 2043715 and 2043716 swapped.
Y.53-02.X2 | 7 | subracks installed
Y.37-01.X6 | 7 | subracks installed
Y.47-01.X6 | 10 | subracks installed
Y.43-01.X6 | 10 | subracks installed
Y.52-01.X6 | 5 | subracks installed
Y.52-04.X7 | 11 | subracks installed
Y.53-04.X7 | 10 | subracks installed
USA side
Y.51-25.X1 | 11 | subracks installed |  | Cables 2048000 and 2047999 swapped.
Y.53-25.X2 | 10 | subracks installed
Y 52-25.X2 | 0 | subracks installed | 10 | subracks in pit next to rack
Y.53-26.X5 | 10 | subracks installed |  |  | 1 | mini subrack
Y.51-26.X5 | 10 | subracks installed |  |  | 1 | mini subrack
Y.51-23.X8 | 4 | subracks installed | 2 | subracks in pit next to rack |  |  | 1 | special subrack
Y.52-23.X8 | 0 | subracks installed | 6 | subracks in pit next to rack |  |  | 1 | special subrack
Y.53-23.X8 | 0 | subracks installed | 3 | subracks in pit next to rack | 4 | standard subracks | 1 | special subrack