## Main Schedule
SCT Cables and Patch Panels
2006-04-26
part-time | done | to be done |  | April |  |  |  | May |  |  |  | June
|  |  | 2006-04-03 | 2006-04-10 | 2006-04-17 | 2006-04-24 | 2006-05-01 | 2006-05-08 | 2006-05-15 | 2006-05-22 | 2006-05-29 | 2006-06-05 | 2006-06-12 | 2006-06-19 | 2006-06-26
Type IV
Installation |  |  | 2006-04-17: 40; 2006-04-24: 80; 2006-06-05: 1402
Acceptance |  |  | 2 shifts | * | Japan | Japan | * | Japan | * | Japan | *
|  |  | * | * | Japan | Japan | * | Japan | * | Japan | *
Test in rack after installation | bar: 2006-04-24 to 2006-06-12
[6 empty] | * | * | * | * | * | * | * | *
Connector in situ by external company - CPE |  |  | 2006-06-26: 2124
Test of cut cables with connector |  |  | Petr | Petr | Petr | Freiburg | * | * | Petr | Petr | * | * | * | Sinica | Sinica | * | *
|  |  | * | Freiburg | * | * | * | * | Prague | Prague | * | * | * | * | * | * | *
Plug-in cables into PS crates + test |  |  | 2006-04-03: Edward; 2006-04-24: Petr; 2006-05-01: Petr; 2006-05-08: Petr; 2006-05-15: Prague; 2006-05-22: Prague; 2006-05-29: Prague | Petr | Prague | Prague
|  |  | 2006-04-03: Stefan; 2006-04-24: JanB; 2006-05-01: JanB; 2006-05-08: JanB; 2006-05-15: Prague; 2006-05-22: Prague; 2006-05-29: Prague | Prague | Prague | Prague
Type II-III
Installation |  |  | 2006-04-17: 616; 2006-04-24: 262; 2006-06-19: 3210
Preparation
| Acceptance + organize cables for installation |  | Vlasti | Vlasti | Vlasti | Vlasti | Vlasti | Vlasti | Vlasti | Vlasti | Vlasti | * | *
|  |  | Martin | Freiburg | * | Geneva | Geneva | Geneva | Geneva | Geneva | * | Glasgow
[6 empty] | Geneva | Geneva | Geneva | Geneva | Geneva | * | Glasgow
| Folding of shield |  | * | * | Neil | Glasgow | * | Glasgow | Freiburg | * | * | * | *
|  |  | * | * | * | Glasgow | TomB | Glasgow | Freiburg | * | * | * | *
[6 empty] | Freiburg | Sinica | Sinica | Sinica | Sinica | Sinica | Sinica | Sinica
Mounting | [5 empty] | Freiburg | * | * | RAL | * | * | RAL | *
Barrel:
Mount dPPB1
Folding the shield foil and cut it the right amount, fix it(old cables)
Squeezing the cables to fit between pin and clamp holder |  |  | Lars | Lars | Lars | * | * | Lars | Lars | Lars | Lars | Lars | Lars
Plug-in of the delicate JST/FCI connectors to dPPB1 |  |  | Neil | Neil | Neil | Neil | Neil | Neil | Neil | Neil | Neil | Neil | Neil
Placing the clamp - arrange drain wire |  |  | * | * | * | * | Pieron | Pieron | Pieron | Pieron | Pieron | Pieron | Pieron
Endcap:
Mount dPPF1 |  |  | 2006-04-03: Lars and Erik are available part time
Prepare drain wires and shield foil during installation
Plug in the dPPF1
Test all cables installed in synch with installation |  |  | Martin | * | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre | Alexandre
Plug-in to PP3 |  |  | * | * | * | * | * | * | Martin | Martin | * | * | * | * | *
PP3
Installation (most of the subracks already installed) | bar: 2006-04-03 to 2006-05-29
Test/Burn-in of units |  |  | 2006-04-03: Scott; 2006-04-10: Scott; 2006-04-17: Scott; 2006-05-15: *; 2006-05-22: *
Assembly into subracks |  |  | 2006-04-03: Edward +1 shift; 2006-04-10: Edward; 2006-04-17: Scott; 2006-05-15: *; 2006-05-22: *
Installation into racks |  |  | Scott | Scott | Scott | * | * | * |  |  | * | *
Plug-in cables to PP3 |  |  |  | 1 shift | * | * | * | * | * | * | * | * | * | *
Type IV | as of March 10, 2100+ cables in US side and 602 cables in USA side already installed - 1522 cables to install since then
Type II-III | 4088 cables | 400 cables/week
Connector in situ by external company - CPE | as of March 10 almost all US side connectors built, to be completed before starting in USA side. Also rack 05 to be reworked, possibly by May 15
PP3 | as of April 20 most of the subracks assembled and installed - see PP3 sheet

## PP3
|  |  |  | to be installed |  | to be assembled
US side
Y.51-02.X2 | 0 | subracks installed | 8 | Subracks in pit next to rack
Y.52-02.X2 | 7 | subracks installed |  | Cables 2043715 and 2043716 swapped.
Y.53-02.X2 | 7 | subracks installed
Y.37-01.X6 | 7 | subracks installed
Y.47-01.X6 | 10 | subracks installed
Y.43-01.X6 | 10 | subracks installed
Y.52-01.X6 | 5 | subracks installed
Y.52-04.X7 | 11 | subracks installed
Y.53-04.X7 | 10 | subracks installed
USA side
Y.51-25.X1 | 11 | subracks installed |  | Cables 2048000 and 2047999 swapped.
Y.53-25.X2 | 10 | subracks installed
Y 52-25.X2 | 0 | subracks installed | 10 | subracks in pit next to rack
Y.53-26.X5 | 10 | subracks installed |  |  | 1 | mini subrack
Y.51-26.X5 | 10 | subracks installed |  |  | 1 | mini subrack
Y.51-23.X8 | 4 | subracks installed | 2 | subracks in pit next to rack |  |  | 1 | special subrack
Y.52-23.X8 | 0 | subracks installed | 6 | subracks in pit next to rack |  |  | 1 | special subrack
Y.53-23.X8 | 0 | subracks installed | 3 | subracks in pit next to rack | 4 | standard subracks | 1 | special subrack