## Plan
| 2005 | [5 empty] | 2006 | [7 empty] | Comments
| Oct |  | Nov |  | Dec |  | Jan |  | Feb |  | March
Shifts*
Type II/III
QA |  | x | x | x | x | x | x | x | x | x | x | x |  |  | Saverio with Pepe and Maarit
Production of double harness |  |  | x | x | x | x | x | x | [6 empty] | company
Delivery of Cable with PP3 connector | [5 empty] | x | x | x | x | x | x | x |  |  | company
Installation | [14 empty] | TC team
Connection to PP3 | [5 empty] | x | x | x | x | x | x | x |  |  | Petr + team
Connection to DPP1 | [5 empty] | x | x | x | x | x | x | x |  |  | Need 5 (experienced) people team
Test with DPP1 dummy load | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 320 | + SCT
Type IV
Delivery |  | x | x | x | x | x
installation US |  | x | x | x | x | x | x | [7 empty] | TC team
Acceptance Test |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [7 empty] | 100 | SCT Collaboration
After Installation Test |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | [5 empty] | 140 | SCT Collaboration
Connector Installation |  |  |  | x | x | x | x | x | x | x |  |  |  |  | company (QA:Petr)
Final cable test |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 400 | SCT Collaboration
PP3
Delivery |  |  |  | x | x | [9 empty] | Melbourne
Test |  |  |  | x | x | x | [8 empty] | Shaun, Igor, Pamela, Ewa
Installation |  |  |  | x | x | x | x | [7 empty] | Ashley, Scott +
DCS cables
typeII |  |  |  |  | 0.5 | [8 empty] | 20 | Richard B. and team
type IV | [6 empty] | 0.5 | [6 empty] | 20 | Richard B. and team
Heather cables |  |  |  |  | 1 | 1 | 1 | [6 empty] | 120 | Terry P.+
*shifts are half day x 2 people | [13 empty] | 1120