# JANUARY

Jan 14 25th Anniversary Gala Committee Meeting

January 14-January 31

Activities/Door Prizes (VOLUNTEER POSITION OPEN)

- Develop list of activities/door prizes and logistics for each

## Catalog (VOLUNTEER POSITION OPEN)

- Review last year’s process

- Are/can we print bidder numbers (large) on back covers?

- Acquire volunteers as needed (see Development Office)

Catalog Advertising (Morris Knight)

- Review last year’s process

- Acquire forms

- Develop list of potential advertisers

Check-out (Leonard and Marylee Levis)

- Check in with Activities/Door Prizes

- Review last year’s process

- Look into computerizing

Clean-up (Ken Pritikin)

- Review last year’s process

- Acquire clean-up team

Decorations (Darril dela Torre)

- Review last year’s process

- Acquire Decorations team and Alternate

- Decorations Kick-off Meeting

Food/Beverages (Heidi Dieffenbach-Carle)

- Review last year’s process

- Are we having anything prepared by parents?

- Meet with I-House to review catering options

- 20 bartenders

Entertainment (Paul Dresher)

- Determine what we want

Getaways/Baskets (Alessandra Ciocio)

- Review last year’s process

- Acquire volunteer team

- Letters to classes/staff

Greeting Table (Gerrie Chui)

- Review last year’s process

- Acquire volunteers

Publicity (OPEN VOLUNTEER POSITION)

- Review last-year’s process

- Develop publicity calendar

- Wire and Bulletin re getaways and special projects

## Setup (OPEN VOLUNTEER POSITION)

- Review last-year’s process with Mark Anderson

- Begin acquiring volunteers

- Develop set-up schedule for days surrounding event

Solicitations (OPEN VOLUNTEER POSITION)

- Develop list of targets

- Acquire solicitation materials

- Acquire volunteers

Special Advertising (Sara Mayeno)

- Develop Special Advertising schedule

Special Class Projects (Rolf Williams)

- Review last year’s process with Natalie Acuna

- Review last year’s materials

- Develop special Class Projects schedule

- Letters to classes/staff

FEBRUARY

# Activities/Door Prizes (VOLUNTEER POSITION OPEN)

Begin acquiring materials

# Catalog (VOLUNTEER POSITION OPEN)

Set up files with Development Office

Review logo

# Catalog Advertising (Morris Knight)

Contact advertisers

# Check-out (Leonard and Marylee Levis)

Review catalog status

# Clean-up (Ken Pritikin)

Review plans

## Decorations (Darril dela Torre)

Acquire materials

# Food/Beverages (Heidi Dieffenbach-Carle)

Meet with Ihouse to walk through event

Firm menu

Acquire beverages

# Entertainment (Paul Dresher)

Contract entertainment

# Getaways/Baskets (Allesandra Ciocio)

Begin production of presentation materials

# Greeting Table (Gerrie Chui)

Establish Greeting Table plan

## Publicity (VOLUNTEER POSITION OPEN)

Wire and Bulletin re getaways and special projects

Invitations designed and produced

Setup (VOLUNTEER POSITION OPEN)

Develop set-up schedule for days surrounding event

Solicitations (VOLUNTEER POSITION OPEN)

Begin solicitations

## Special Advertising (Sara Mayeno)

Keep abreast of getaways and special projects

# Special Class Projects (Rolf Williams)

Begin production

# Volunteer Coordinator/Development (Alan Fox/Development Office)

Touch base with Ihouse

Confirm parking

Plan auction logistics

Staff solicitation

MARCH

# Activities/Door Prizes (VOLUNTEER POSITION OPEN)

- Acquire materials

Catalog Setup (VOLUNTEER POSITION OPEN)

- Production

# Catalog Advertising (Morris Knight)

- Continue to contact advertisers

- Feed materials to catalog production—deadline is early April

# Check-out (Leonard and Marylee Levis)

- Firm check-out plan

# Clean-up (Ken Pritikin)

- Review plans

## Decorations (Darril dela Torre)

- Acquire materials

- Walk through with Ihouse

# Food/Beverages (Heidi Dieffenbach-Carle)

- Continue to acquire beverages

- Consider supplemental serving needs

Entertainment (Paul Dresher)

- Walk through with Ihouse

# Getaways/Baskets (Alessandra Ciocio)

- March 15 is deadline for ideas

- Continue production of presentation materials

# Greeting Table (Gerrie Chui)

- Firm plan

## Publicity Setup (VOLUNTEER POSITION OPEN)

- Invitations mailed late March for RSVP April 30

## Setup (VOLUNTEER POSITION OPEN)

- Establish plan with Decorations, Food/Beverages, and Entertainment

Solicitations (VOLUNTEER POSITION OPEN)

- Continue

- Remind all to return Donor Certificates to Development Office

## Special Advertising (Sara Mayeno)

- Begin advertising getaways and special projects

# Special Class Projects (Rolf Williams)

- March 15 is deadline for ideas

- Continue production

## Volunteer Coordinator/Development (Alan Fox)

- Firm auction logistics

- Mailing list to publicity by early March

- 8th grade sign ups

APRIL

## Activities/Door Prizes (VOLUNTEER POSITION OPEN)

- All in place

- Walk through with Set-up

- Determine day-of-event person

Catalog (VOLUNTEER POSITION OPEN)

- Complete production and to print after advertising, getaways and special projects are all in

- Catalog to print

- Determine day-of-event person

Catalog Advertising (MORRIS KNIGHT)

- Send copies of catalogs to advertisers

Check-out (VOLUNTEER POSITION OPEN)

- Walk through check-out plan

- Determine day-of-event person

Clean-up (Ken Pritikin)

- Walk through plans

- Determine day-of-event person

Decorations (Darril dela Torre)

- Establish day-of-event plan

- Determine day-of-event person

Food/Beverages (Heidi Dieffenbach-Carle)

- Establish day-of-event plan

- Determine day-of-event person

Entertainment (Paul Dresher)

- Establish day-of-event plan

- Determine day-of-event person

Getaways/Baskets (Alessandra Ciocio)

- Continue production of presentation materials

- Establish day-of-event plan

- Determine day-of-event person

Greeting Table (Gerrie Chui)

- Establish day-of-event plan

- Determine day-of-event person

Publicity (VOLUNTEER POSITION OPEN)

- Reminder flyers

- Posters

Setup (VOLUNTEER POSITION OPEN)

- Establish day-of-event-plan

- Determine day-of-event person

Special Advertising (Sara Mayeno)

- Facilitate transferring displays to Ihouse

Special Class Projects (Rolf Williams)

- Facilitate transferring items to IHouse

- Determine day-of-event person

Volunteer Coordinator/Development (Alan Fox/Development Office)

- General facilitation