Windrush Annual Fundraising Event

April 30, 2005

A Guide to the Auction Committees:

Mission, Tasks, and Schedule

of

The Auction Coordination Committee

with

Solicitations

Food&Drink

Art Class Projects

Site Logistics

Catalog

Office Support

Publicity

8th Graders

------------------------------------------------------------------------------

Alessandra Ciocio 					March 1, 2005

Auction Coordination

Committee Chair:	Alessandra Ciocio

Development Office:	Thea Daniels, Melissa Vainio

Responsibilities:	Coordinate all aspect of the Auction Event with all Committees: Solicitations, Food&Drink, Class art projects, Site logistics, Catalog, Office support, Publicity, 8th graders work

- Secure the site where to host the Auction

- Define the theme and the name for the event

- Find all the volunteers to chair/work for the Auction

- Follow-up all activities carried out by every Subcommittee to ensure the completion on schedule of every task

- Review item classification with the Solicitations Committee Chair and with the Development Office

.

Members: WPA, Subcommittee Chairs, and Development Office

(open to anyone who volunteers for the Auction)

Subcommittees_	_Chairs____

Solicitations		Jen Villeneuve

Food&Drink		Lucy Aghadjian

Art Projects		Emily Payne

Site Logistics		Alessandra Ciocio

Inventory & Catalog	Sara Mayeno

Office Support	Kathy Lee

Publicity		Sarah Johnson

8th Graders		Darril dela Torre

Schedule:

Nov/Jan	Find all the volunteers to fulfill every task.

January 20	Define Theme and Name for the event.

Jan/April	Monthly General Meetings (open to everyone) with all Committee

members and Subcommittees Chairs (and Chairs of Subcommittees

splits).

One on one communication (frequent email, phone calls) especially on approaching deadlines, or to discuss the job at an early stage.

Meetings at the school or offsite with individual Chairs when needed. Last week before the Event, review all operations including rehearsal of crucial parts of the event (check-out procedure, for instance) and review agenda of set-up day.

Make a Check list.

April 30, 2005		Windrush Annual Auction Party

Solicitations Committee

Committee Chair:		Jen Villeneuve

Responsibilities:      Organize the acquisition of items to be sold at the event and Sponsorship donations.

- Revise and prepare letters and donation forms to distribute to merchants. Mail-out the letters.

- Organize volunteers into different areas for business solicitations.

- Communicates regularly with committee members on their progress in the solicitation and acquisition of items and to make sure they are following the schedule

- Select items to go into live auction, silent auction, and the prizes and in consultation with Auction Chair and Development team.

- Turn donation forms to Catalog Chair so items can be entered in the inventory.

- Coordinate with Catalog storage of items.

The items include:

Donations from merchant

Getaways, a collection of certificates such as hotel, B&B, SPA, tours, etc., for a weekend or a day.  Those are obtained from private donations or by soliciting discount or donation from the vendors. Getaway items are usually included in the silent auction with special large display boards to explain the package or go in the live auction.

School wish list by which people can directly donate towards an item requested by teachers

Pick-a-party: this year we are also introducing these special events items: 20 to 30 events hosted by Windrush families.  The events are set for a specific date & time, a number of people who can attend and the price for the event.  The hosts are responsible for the details, costs, and location of their events.

Sponsorship:  Monetary donations in exchange for sponsorship and advertising recognition at the event and in the catalog. This entails asking businesses that might not have a tangible product to donate to sponsor at different levels.

This committee coordinates with Catalog and Publicity committees.

If items are received by this committee turn them to Catalog Committee

Schedule:

Jan/Feb 	Communicate weekly progress of acquisition with Auction Chair and Development Office

Feb 5	Mail out solicitation letters

Feb/March	Regularly turn in donation descriptions to Catalog Chair

February 28	Preliminary report on all items obtained

March 25	Final report with description of all items to Catalog and all donation forms to Development Office

Food & Drinks

Committee Chair:		Lucy Aghadijan

Responsibilities:  	Coordinate all food and drink for the event

- Determine the items to be donated or the items to be purchased.

- If the on-site caterer is used, coordinates food&drink with the Auction site manager through Auction Chair and Development Office.

This committee coordinates with the Solicitations committee for the donations and purchases, and with the Catalog committee for final presentation of the menu in the Auction Program (Catalog).

Schedule:

February 15	Review menu with Auction Coordination/Chair and propose changes.

Compile list of donations and purchases.

February 28	Final Proposal

Art Class Projects

Committee Chair:		Emily Payne

Responsibilities: 	Organize and facilitate the creation of art projects from each class (group efforts) to be auctioned off. Each class needs a representative to help, and the chair oversees the effort in accordance with a theme or vision.

- Contact parent volunteers to discuss project ideas for each grade

- Select projects for each class and review them with Auction, and the Solicitations Committee Chairs

- Ensure that parent’s volunteers will follow a schedule

- Oversee and facilitate completion of projects

- Decide (in coordination with Set-up Chair and Logistics Chair) how to set-up projects at the event

- Help on Set-up day to make sure projects are

displayed correctly

Members:

| Zephyrs |  |
| --- | --- |
| Sprites |  |
| Alvens |  |
| Hobbits |  |
| Comets |  |
| Antares |  |
| Unicorns |  |
| Griffins |  |
| Phoenix-6 |  |
| Phoenix-7 |  |
| Phoenix-8 |  |

Schedule:

January 26		Identify volunteers from each class

February 15		Select projects and report status to Auction Chair

March 25	Compile final report with description of each item

April 1	Complete projects

Site Logistics

Committee Chair: 	Alessandra Ciocio

Responsibilities:	Coordinate all the operations that will take

place at the Auction site

- Work on all the arrangements with the Auction site

- Determine requirements for set-up.

- Produce plan on layout and usage of the rooms and optimal flow of the event.

- Plan and implement decorations (with the help of Publicity Committee).

- Review with Auction Coordination/Chair the program of the evening and plan for the music to play according to the theme or what is appropriate to different parts of the evening.

- Organize Greeting and check-out tables.

- Make a list of all extra items to be transported to the Auction site (besides the auction items).

- Coordinate transportation of all items on the day of the event, set-up and staging of items, and clean-up.

- Produce agenda for set-up day.

Subcommittees and tasks:

Site arrangements	Alessandra, Jen, Thea

Set-up			Erin Uesugi

Decorations

Greeting Tables

Check-out Tables	Anna Weisberg

Clean-up		Doug Clough (?)

Transportation

This committee works with the ALL Committees Chairs to determine requirements related to set-up, decorations, and any other operation at the event.

Schedule:

Jan 26		Find all the volunteers to take on the various tasks

Jan/Feb	Determine Decoration and requirements for set-up

February 18	Complete plan for Music to review with Auction Coordination/Chair

Feb 25		Complete set-up plan

Feb 28		Finalize agreement with Auction site

March 25	Complete Decorations

April 8		Final Review of the plan and flow of the event with all the volunteers in

this committee

April 25	Rehearsal of check-out procedure with volunteers

April 30	Transportation of all items and set-up starting in the morning

Catalog

Committee Chair:	Sara Mayeno

Responsibilities:	Work on Inventory and Catalog

- Work on tracking auction items (inventory) in coordination with Solicitations Committee.

- Enter items data into database, and organize items (list and storage) as they come in.

- Produce the catalog (paper and online) with help from Publicity Committee

- Prepare list of auction items to be transported to the Auction site.

- Coordinate with Logistics Committee to determine space needed for the display of items.

- Check-out data entry

Subcommittees and tasks:

Inventory/Catalog	Peggy Scott

Philippa Kelley

Software Manager

This Committee coordinates with Solicitations, Publicity, and Logistics Committees

Schedule:

February	Get familiar with Database program and start to enter the

items in the Inventory

March 25	All items are in

April 8		Inventory completed

April 12-13	Catalogs are printed (to go in the 4/14 Thursday Packet)

April 22	Experience of check-out data entry

Office Support

Committee Chair:	Kathy Lee

Responsibilities:	General office assistance

- Work with Publicity Committee to prepare and mail out invitations

- Prepare envelopes for gift certificates

- Prepare bid sheets

- Produce fliers/signs

Subcommittees and tasks:

Invitations		Susan Brand

Envelopes for gift

Bid sheets		Kathy Lee

Signs/fliers

This Committee coordinates with Solicitations, Publicity, and Catalog Committees.

Schedule:

March 18 	Complete/print invitations

March 22	mail out invitations

March 25	Now on dynamically produce fliers/signs to announce special items

April 22	Produce envelopes for gift certificates and bid sheets

Publicity

Committee Chair:	Sarah Johnson

Responsibilities:	Work on the design and marketing

- Work with the Auction Coordination/Chair, and the Development Office to determine the right design for the logo and strategy of marketing.

- Design Invitations and work with Office Support that will produce them

- Design fliers/banners and place them around the school, in Thursday packets, Windrush Wire, etc., to raise awareness of the event and advertise items going to auction.

- Work with Catalog Committee to help with the design of the Program (catalog).

- Work with Solicitations Committee to obtain the list of items that need to be publicized (with fliers, etc.) before the Auction.

- Design and produce Display Boards for special items in coordination with Solicitations/Catalog Committees.

- Design and produce signs that could be used at the Auction Event in coordination with Logistics Committee.

- The auctioneer review live items with Auction Chair and Development Office.  Prepare for the show!

Subcommittees and tasks:

Logo Design 		Susan Brand

Signs/Fliers		Ellie Jacobson

Display Boards	Leigh Kienker

Auctioneer		Bob Zimmerman

This committee coordinates with the Office Support, Solicitations, Catalog and Logistics Committees and the Development Office.

Schedule:

January 25	Review ideas for the Design of logo with Auction Coordination/Chair

January 25	Discuss strategy of marketing with Auction Coordination/Chair

February 4	First announcement on Thursday Packet of the upcoming event

Announcement on Thursday Packets will appear biweekly or on

demand by consulting with Auction Coordination and Solicitations

committee chairs.

March 1	Create Logo

March 25	Now on dynamically design fliers/signs to announce special items

April 14	Completion of Display Boards for large items and Signs for the Auction

April 26	Auctioneer meets with Auction Chair and Development Office

8th graders Coordination

Committee Chair:		Darril dela Torre

Responsibilities:	Coordinate 8th graders work at the Event

List of jobs:

(Tentative)

- Greeting guests (take coats, direct guests to greeting table)

- Sell prizes (balloons, magic wands)

- Help with logistics (moving chairs, tables)

- Distribute sold items to winners

Schedule:

February 25	Propose plan to Auction Committee/Chair

March 1 	Produce the list of 8th graders who will work at the Event.

March 25	Produce final Plan of jobs

March 28	Lunch with 8th grader to go over duties and questions