Windrush Annual Fundraising Event

April 30, 2005

A Guide to the Auction Committees:

Mission

Tasks

Schedule

of

Auction Coordination

Solicitations	       Site Logistics

Art Class Projects				  Publicity

Food&Drink    		Office Support

8th Graders

------------------------------------------------------------------------------

Alessandra Ciocio 					Draft, January 2005

Auction Coordination

Committee Chair:	Alessandra Ciocio

Development Office:	Thea Daniels, Melissa Vainio, Ellen Becherer

Responsibilities:	- Coordinate all aspect of the Auction Event:

Solicitations, Food&Drink, Site logistics, Class art projects, Office support, Publicity, 8th graders work

- Secure the site where to host the Auction

- Define the theme and the name for the event

- Find all the volunteers to chair/work for the Auction

- Follow-up all activities carried out by every Subcommittee to ensure the completion on schedule of every task

-  Review item classification with Solicitations Committee Chair and with the Development Office

.

Members: WPA, Subcommittee Chairs, and Development Office

(open to anyone who volunteers for the Auction)

Subcommittees_	_Chairs____

Solicitations		Jen Villeneuve

Food&Drink		Lucy Aghadjian

Site Logistics		Alessandra Ciocio

Art Projects		Emily Payne

Office Support	Sara Mayeno

Publicity		Sarah Johnson

8th Graders		Darril dela Torre

Schedule:

Nov/Jan	Find all the volunteers to fulfill every task.

January 20	Define Theme and Name for the event.

Jan/April	Monthly General Meetings (open to everyone) with all Committee

members and Subcommittees Chairs (and Chairs of Subcommittees

splits).

One on one communication (frequent email, phone calls) especially on approaching deadlines, or to discuss the job at an early stage.

Meetings at the school or offsite with individual Chairs when needed. Last week before the Event, review all operations including rehearsal of crucial parts of the event (check-out procedure, for instance) and review agenda of set-up day.

Make a Check list. (checked!)

April 30, 2005		Windrush Annual Auction Party

Solicitations Committee

Committee Chair:		Jen Villeneuve

Responsibilities:	- Organize the acquisition of items to be sold at the event

and Sponsorship donations.

- Select items to go into live auction, silent auction, and the wandering prizes.

The items include:

Direct merchant solicitations (mail, phone, in person)

Getaways, a collection of certificates such as hotel, B&B, SPA, tours, etc., for a weekend or a day.  Those are obtained from private donations or by soliciting discount or donation from the vendors. Getaway items are usually included in the silent auction with special large display boards to explain the package or go in the live auction.

School wish list by which people can directly donate towards an item requested by teachers

Pick-a-party: this year we are also introducing these special events items: 20 to 30 events hosted by Windrush families.  The events are set for a specific date & time, a number of people who can attend and the price for the event.  The hosts are responsible for the details, costs, and location of their events.

Sponsorship Seek monetary donations in exchange for sponsorship and advertising recognition at the event and in the catalog. This entails asking businesses that might not have a tangible product to donate to sponsor at different levels.

Tasks for merchant solicitations:

- Revise and prepare letters and donation forms to distribute to merchants

- Organize volunteers into different areas for business solicitations

- Committee Chair communicates regularly with committee members on

their progress in the solicitation and acquisition of items and to make sure

they are following the schedule

- Turn donation forms into Office Support Chair so items can be

tracked and categorized

This committee coordinates with Office Support and Publicity committees.

If items are received by this committee turn them to Office Support/Inventory Committee

Schedule:

Jan/Feb 		Communicate weekly progress of acquisition with

Auction Chair and Development Office

Feb/March		Regularly turn donation forms/description and actual

items to Office Support Chair

February 28		Preliminary report on all items obtained

March 25		Final report with description of all items

Turn all donation forms and items to Office Support

Food & Drinks

Committee Chair:		Lucy Aghadijan

Responsibilities:  Coordinate all food and drink for the event. Determine 
the items to be donated or the items to be purchased. If the on-site caterer is used, coordinates food&drink with the Auction site manager through Auction Chair and Development Office.

This committee coordinates with Solicitations committee for the donations and purchases, and with Office Support committee for final presentation of the menu in the Auction Program (Catalog).

Schedule:

February 15	Review menu with Auction Coordination/Chair and propose changes.

Compile list of donations and purchases.

February 28	Final Proposal

Art Class Projects

Committee Chair:		Emily Payne

Responsibilities: 	Organize and facilitate the creation of art projects
from each class (group efforts) to be auctioned off. Each class needs a representative to help, and the chair oversees the effort in accordance with a theme or vision.

- Contact parent volunteers to discuss project ideas for each grade

- Select projects for each class and review them with Auction, and the Solicitations Committee Chairs

- Ensure that parent’s volunteers will follow a schedule

- Oversee and facilitate completion of projects

- Decide (in coordination with Set-up Chair and Logistics Chair) how to set-up projects at the event

- Help on Set-up day to make sure projects are

displayed correctly

Members:

| Zephyrs |  |
| --- | --- |
| Sprites |  |
| Hobbits |  |
| Comets |  |
| Antares |  |
| Unicorns |  |
| Griffins |  |
| Phoenix-6 |  |
| Phoenix-7 |  |
| Phoenix-8 |  |

Schedule:

January 26		Identify volunteers from each class

February 15		Select projects and report status to Auction Chair

March 25	Compile final report with description of each item

April 1	Complete projects

Site Logistics

Committee Chair: 	Alessandra Ciocio

Responsibilities:	- Coordinate all the operations that will take place at the

Auction site

- Work on all the arrangements with the Auction site

- Determine requirements for set-up.

- Produce plan on layout and usage of the rooms and optimal flow of the event.

- Plan and implement decorations (with the help of Publicity Committee).

- Review with Auction Coordination/Chair the program of the evening and plan for the music to play according to the theme or what is appropriate to different parts of the evening.

- Organize Greeting and check-out tables.

- Make a list of all extra items to be transported to the Auction site (besides the auction items).

- Coordinate transportation of all items on the day of the event, set-up and staging of items, and clean-up.

- Produce agenda for set-up day.

Subcommittees and tasks:

Site arrangements	Alessandra, Jen, Thea

Set-up			Erin Uesugi

Decorations

Greeting Tables

Check-out Tables	Anna Weisberg

Clean-up		Doug Clough (?)

Transportation

This committee works with the ALL Committees Chairs to determine requirements related to set-up, decorations, and any other operation at the event.

Schedule:

Jan 26		Find all the volunteers to take on the various tasks

Jan/Feb	Determine Decoration and requirements for set-up

February 18	Complete plan for Music to review with Auction Coordination/Chair

Feb 25		Complete set-up plan

Feb 28		Finalize agreement with Auction site

March 25	Complete Decorations

April 8		Final Review of the plan and flow of the event with all the volunteers in

this committee

April 30	Transportation of all items and set-up starting in the morning

Office Support

Committee Chair:	Sara Mayeno

Responsibilities:	- General office assistance.

- Work on tracking auction items (inventory) in coordination with Solicitations Committee.

- Enter items data into database, and organize items (list and storage) as they come in.

- Produce the catalog (paper and online).

- Design (with Publicity Committee), prepare and mail out invitations.

- Prepare envelopes for gift certificates.

- Prepare bid sheets.

- Prepare list of auction items to be transported to the Auction site.

- Coordinate with Logistics Committee to determine space needed for the display of items and the transportation of items from storage to Auction site.

- Coordinate the procedure used by the check-out team to record purchases.

Subcommittees and tasks:

Inventory

Catalog		Kathy Lee

Invitations

Envelopes for gift

Bid sheets		Kathy Lee

Check-out		Anna Weisberg

This Committee coordinates with Solicitations, Publicity, and Logistics Committees

Schedule:

February	Get familiar with Database program and start to enter the

items in the Inventory

March 18 	Complete/print invitations

March 22	mail out invitations

March 25	All items are in

April 8		Inventory completed

April 12-13	Catalogs are printed (to go in the 4/14 Thursday Packet)

April 22	Produce envelopes for gift certificates and bid sheets

April 25	Rehearsal of check-out procedure with volunteers

Publicity

Committee Chair:	Sarah Johnson

Responsibilities:	- Work on the design and marketing.

- Design and produce fliers/banners and place them around the school, in Thursday packets, Windrush Wire, etc., to raise awareness of the event and advertise items going to auction.

- Work with the Auction Coordination/Chair, and the Development Office to determine the right design for the logo and strategy of marketing.

- Work with Office Support Committee to help with the design of the Program (catalog) and Invitations.

- Work with Solicitations Committee to obtain the list of items that need to be publicized (with fliers, etc.) before the Auction.

- Design and produce Display Boards for special items in coordination with Solicitations/Office Support Committees.

- Design and produce signs that could be used at the Auction Event in coordination with Logistics Committee.

- The auctioneer review live items with Auction Chair and Development Office.  Prepare for the show!

Subcommittees and tasks:

Logo Design 		Susan Brand

Signs/Fliers

Display Boards

Auctioneer		Bob Zimmerman

This committee coordinates with Office Support, Solicitations, and Logistics Committees and the Development Office.

Schedule:

January 25	Review ideas for the Design of logo with Auction Coordination/Chair

January 25	Discuss strategy of marketing with Auction Coordination/Chair

February 4	First announcement on Thursday Packet of the upcoming event

Announcement on Thursday Packets will appear biweekly or on

demand by consulting with Auction Coordination and Solicitations

committee chairs.

March 1	Create Logo

March 25	Now on dynamically produce fliers/signs announcing special items

April 14	Completion of Display Boards for large items and Signs for the Auction

April 26	Auctioneer meets with Auction Chair and Development Office

8th graders Coordination

Committee Chair:		Darril dela Torre

Responsibilities:	Coordinate 8th graders work at the Event.

List of jobs:

(Tentative)

- Greeting guests (take coats, direct guests to greeting table)

- Sell wandering prizes (balloons, pick-an-apple)

- Help with logistics (moving chairs, tables)

- Distribute sold items to winners

Schedule:

February 25	Propose plan to Auction Committee/Chair

March 1 	Produce the list of 8th graders who will work at the Event.

March 25	Produce final Plan of jobs